## version current
Sr No. | Screen Number | Screen Name | Iteration -1 : Issue/Defect Detail | Status | Iteration -2 : Issue/ Defect Details | Status | Iteration -3 : Issue / Defect Details
1 | Globally | Globally | Inconsistent slide transcript button naming. | close
2 | Globally | Globally | screen Page number are inconsistent. | close
3 | Globally | Globally |  |  |  | Open | the text ' click the forward arrow to continue' is missing in transcript.
4 | Globally | Globally | The resource button in the app works fine, but the content it shows is not related to the topic. Also, when you click on the link or content, it doesn't take you to the right extra information page or any related page. | Reopen | The resource button in the app works fine, but the content it shows is not related to the topic. | Reopen | Resource button has been disabled.
5 | Globally | Globally | Close button disabled. | Reopen | Close button disabled. | Reopen | Close button disabled.
6 | Globally | Globally | Active Forward Button During Content Play. | Reopen |  | close
7 | 1 | Introduction to di-isocyanates | transcript different and button name different.transcript button name shown "T "instead "cc" | partially close | In the help button content, the button name "cc" for transcript needs to be changed to "T". | Reopen | In the help button content, the button name "cc" for transcript needs to be changed to "T".
8 | 1 | Introduction to di-isocyanates | every sentence on screen not vertical align to the other sentence text. | close | the popup of the note does not disappear | close
9 | 1 | Introduction to di-isocyanates | Active forward button during content play. | Reopen | Active forward button during content play. | close
10 | 1 | Introduction to di-isocyanates | the text not vertical align on screen. | close
11 | 1 | Introduction to di-isocyanates | All chapter thumbnail image is missing. | Reopen | All chapter thumbnail image is missing. | close
12 | 2 | Module objectives | All chapter box text are not horizantally align with each other. | Reopen | All chapter box text are not horizantally align with each other. | close
13 | 2 | Module objectives | The sentence "Select a chapter to proceed" is missing from the screen. | close
14 | 3 | Sub-menu | All chapter thumbnail image is missing. | Reopen | All chapter thumbnail image is missing. | close
15 | 3 | Sub-menu | All chapter box text are not horizantally align with each other. | Reopen | All chapter box text are not horizantally align with each other. | close
16 | 3 | Sub-menu | The sentence "Select a chapter to proceed" is missing from the screen. | Reopen | The sentence "Select a chapter to proceed" is missing from the screen. | close
17 | 3 | Sub-menu | The replay button is not working or unclickable | Reopen | The replay button is not working or unclickable | Reopen | The replay button is not working or unclickable
18 | 3 | Sub-menu | headline of the content text must be bold in size. | Reopen | headline of the content text must be bold in size. | close
19 | 3 | Sub-menu | can we increase text font size of topic . The font size of the topic name is too small, making it difficult to read. | close
20 | 3 | Sub-menu | the chapter boxes color are inconsistent. Shown in gray color some time. | Reopen | The chapter box is unclickable, meaning it cannot be selected or interacted with it | close | In the changed functionality, the chapter serial-wise box is only activated up to the first completed chapter.
21 | 4 | Chapter 1: | active forward button during content play | Reopen | active forward button during content play | close
22 | 5 | What are di-isocyanates? | transcript content is different on screen. | Reopen | transcript content is different on screen. | close
23 | 5 | What are di-isocyanates? | the content text should be placed below the image. | open | There is inconsistency between the location of images and text. They are not consistently placed in the same positions throughout the content. | open | There is inconsistency between the location of images and text. They are not consistently placed in the same positions throughout the content.
24 | 5 | What are di-isocyanates? | the content in resource button is not related to the topic | Reopen | the content in resource button is not related to the topic | Reopen | Resource Button Content and Navigation Issue ,button is disabled.
25 | 6 | Reactivity of di-isocyanates | The headline content text should be positioned on top and in the center of the slide. | Reopen | The headline content text should be positioned on top and in the center of the slide. | Reopen | The headline content text should be positioned on top and in the center of the slide.
26 | 6 | Reactivity of di-isocyanates | The image size is larger than the expected or intended size. | Reopen | The image size is larger than the expected or intended size. | Reopen | The image size is larger than the expected or intended size.
27 | 6 | Reactivity of di-isocyanates | The image location and the content related to it have been changed from left to right (or vice versa) as per the storyboard. | Reopen | The image location and the content related to it have been changed from left to right (or vice versa) as per the storyboard. | Reopen | The image location and the content related to it have been changed from left to right (or vice versa) as per the storyboard.
29 | 6 | Reactivity of di-isocyanates |  |  |  | Open | AS per storynboard , functional flow of Ovice over and OST1 and image 1 is not being followed.The expected sequence and behavior outlined in the storyboard are not being followed.
30 | 7 | Hazard communication | image is large found. | Reopen | image is large found. | Reopen | The image size is larger than the expected or intended size.
31 | 7 | Hazard communication |  |  |  | Open | the forward button is active during content play.
32 | 7 | Hazard communication |  |  |  | Open | the screen page number is inconsistent. Need to page number 7 out off 38 but found is 8/38.
33 | 7 | Hazard communication | first topic thumbnail image slightly shift to upward, not align other image. | close.
34 | 7 | Hazard communication |  | open | click to next content' ,the voice starts playing in between the content play at last topic . | Reopen | 'click to next content' ,the voice starts playing in between the content play at last topic .
35 | 8 | Identification of di-isocyanates |  |  |  | Open | page number is inconsistent. Number should be 8/38.
36 | 9 | Irritants from di-isocyanates |  |  |  | Open | the content text fonts and image size is larger found.
37 | 9 | Irritants from di-isocyanates |  |  |  | Open | text font is large. Should be consitent in all over application.
38 | 9 | Irritants from di-isocyanates |  |  |  | Open | The image size is larger than the expected or intended size.
39 | 9 | Irritants from di-isocyanates |  |  |  | Open | There is inconsistency between the location of images and text. They are not consistently placed in the same positions throughout the content.The image location and the content related to it have been changed from left to right (or vice versa) as per the storyboard.
40 | 9 | Irritants from di-isocyanates | The note prompt box is missing from the screen. | Reopen | The note prompt box is missing from the screen. | close
41 | 9 | Irritants from di-isocyanates |  |  |  | open | page number is inconsistent. Number should be as per serial wise.
42 | 9 | Irritants from di-isocyanates | The note prompt box for this slide is separately published . | Reopen | The note prompt box for this slide is separately published . | close
43 | 10 | Risk of exposure | content image is missing. | close |  | Open | The image location and the content related to it have been changed from left to right (or vice versa) as per the storyboard.
44 | 10 | Risk of exposure |  |  |  | Open | the text of image caption is not align with other other image caption.
45 | 10 | Risk of exposure | image missing. | close |  | Open | the note box width size need to be increase .the note box width size is inconsistent.
46 | 11 | Factors of risk |  |  |  | Open | page number is inconsistent. Number should be as per serial wise.
47 | 11 | Factors of risk |  |  |  | Open | text color is slightly different ,you may say text color light.
48 | 3 | sub-menu | chapter The image size is larger than the expected or intended size.. image is missing and color inconsistent. | Reopen | chapter The image size is larger than the expected or intended size.. image is missing and color inconsistent. | close
49 | 12 | chapter-2 |  | open | unclickable,it cannot be selected or interacted with it | close
50 | 13 | Sensitization and exposure protection
51 | 14 | can you rely on odor |  |  |  | Open | In transcript text 'Odor' word should be change as 'odor'.
52 | 14 | can you rely on odor
53 | 14 | can you rely on odor
54 | 14 | can you rely on odor
55 | 14 | can you rely on odor
56 | 15 | phase on sensitization | the color should be used as per customer guide line. | Reopen | the color should be used as per customer guide line. | Reopen | the phase boxes color are inconsistent
57 | 15 | phase on sensitization | the heading sentence ' the signs of sensitization devlope in three phase' of the topic is missing on the screen. | Reopen | the heading sentence ' the signs of sensitization devlope in three phase' of the topic is missing on the screen. | close
58 | 16 | Preventing sensitization to di-isocyanates | slide missing | Reopen | slide missing | close
59 |  |  | slide missing | Reopen | slide missing | close
60 | 17 | Measures to prevent exposure |  |  |  | close
61 | 17 | Measures to prevent exposure |  |  |  | Open | the on screen text fonts size is larger found . Inconsistent in OST size .
62 | 17 | Measures to prevent exposure | extra tabs are seen. | close |  | Open | transcript is different on screen.the content displayed is unrelated to the topic
63 | 17 | Measures to prevent exposure | forward button active during content run. It should be active after all tab click. | close |  | Open | After click on the topic 'skin body exposure' as expected work but the on screen text font size is inconsistent to eachother also color of text is inconsitent .
64 | 17 | Measures to prevent exposure |  |  |  | Open | hand and eye exposure' work as expected. But OST and icon are not horizontal align .
65 | 17 | Measures to prevent exposure
66 | 18 | Use of filters in Respiratory Protective Equipment (RPE) | slide missing | close |  | open | as per storyboard , page content design not found.
67 | 18 | Use of filters in Respiratory Protective Equipment (RPE) | slide missing | close |  | open | Do and Don't content slide is missing
68 | 19 | how to take off gloves without contamination |  |  |  | open | the on screen text fonts size is larger found . Inconsistent in OST size .